## Shipments
Shipment ID | Forwarder | Mode | Origin | Destination | Ship Date | Promised Delivery | Actual Delivery | Status | Priority | Last Update | Notes
SHP-1001 | Kuehne+Nagel | Ocean | Rotterdam, NL | Haifa DC | 2026-09-14 | 2026-10-06 | 2026-10-05 | Delivered | Medium | 2026-10-05 | Delivered on time
SHP-1002 | DHL Global Forwarding | Air | Portland, US | Petah Tikva DC | 2026-10-03 | 2026-10-07 | 2026-10-08 | Delivered | High | 2026-10-08 | Delivered 1 day late - customs inspection
SHP-1003 | DB Schenker | Ocean | Shanghai, CN | Kiryat Gat Fab | 2026-09-10 | 2026-10-08 |  | Delayed | High | 2026-10-07 | Vessel held at port of Piraeus, new ETA Oct 15
SHP-1004 | Expeditors | Air | Phoenix, US | Kiryat Gat Fab | 2026-10-06 | 2026-10-10 |  | In Transit | High | 2026-10-08 | On schedule
SHP-1005 | UNIC Logistics | Inland | Ashdod Port | Jerusalem DC | 2026-10-07 | 2026-10-09 |  | In Transit | Medium | 2026-10-07 | Truck dispatched, no update since dispatch
SHP-1006 | Kuehne+Nagel | Ocean | Antwerp, BE | Haifa DC | 2026-09-20 | 2026-10-12 |  | In Transit | Low | 2026-10-06 | Vessel on schedule
SHP-1007 | DHL Global Forwarding | Air | Penang, MY | Haifa DC | 2026-10-05 | 2026-10-08 |  | At Customs | High | 2026-10-08 | Missing commercial invoice - customs hold
SHP-1008 | Expeditors | Air | Leixlip, IE | Kiryat Gat Fab | 2026-10-01 | 2026-10-04 | 2026-10-04 | Delivered | Medium | 2026-10-04 | Delivered on time
SHP-1009 | DB Schenker | Inland | Haifa Port | Haifa DC | 2026-10-08 | 2026-10-09 |  | Pending Pickup | Medium | 2026-10-08 | Driver not assigned yet
SHP-1010 | Kuehne+Nagel | Air | Hillsboro, US | Petah Tikva DC | 2026-10-04 | 2026-10-08 |  | In Transit | High | 2026-10-06 | Connecting flight missed in Frankfurt
SHP-1011 | UNIC Logistics | Inland | Kiryat Gat Fab | Jerusalem DC | 2026-10-02 | 2026-10-03 | 2026-10-03 | Delivered | Low | 2026-10-03 | Delivered on time
SHP-1012 | DB Schenker | Ocean | Busan, KR | Kiryat Gat Fab | 2026-09-05 | 2026-10-02 | 2026-10-07 | Delivered | High | 2026-10-07 | Delivered 5 days late - port congestion
SHP-1013 | Expeditors | Air | Chandler, US | Haifa DC | 2026-10-07 | 2026-10-11 |  | In Transit | Medium | 2026-10-08 | On schedule
SHP-1014 | DHL Global Forwarding | Ocean | Hamburg, DE | Haifa DC | 2026-09-22 | 2026-10-14 |  | In Transit | Low | 2026-10-05 | On schedule
SHP-1015 | Kuehne+Nagel | Inland | Ashdod Port | Kiryat Gat Fab | 2026-10-06 | 2026-10-07 |  | At Customs | High | 2026-10-09 | Customs released today, awaiting truck
SHP-1016 | UNIC Logistics | Air | Kulim, MY | Kiryat Gat Fab | 2026-10-03 | 2026-10-06 | 2026-10-06 | Delivered | Medium | 2026-10-06 | Delivered on time
SHP-1017 | DB Schenker | Air | Dalian, CN | Petah Tikva DC | 2026-10-08 | 2026-10-12 |  | In Transit | Medium | 2026-10-08 | On schedule
SHP-1018 | Expeditors | Ocean | Valencia, ES | Haifa DC | 2026-09-25 | 2026-10-10 |  | Delayed | Medium | 2026-10-08 | Vessel delayed by weather, new ETA Oct 13
SHP-1019 | DHL Global Forwarding | Inland | Petah Tikva DC | Haifa DC | 2026-10-08 | 2026-10-08 |  | In Transit | High | 2026-10-08 | Urgent spare parts, truck en route
SHP-1020 | Kuehne+Nagel | Air | Santa Clara, US | Jerusalem DC | 2026-10-02 | 2026-10-05 | 2026-10-05 | Delivered | Low | 2026-10-05 | Delivered on time
SHP-1021 | UNIC Logistics | Ocean | Singapore, SG | Kiryat Gat Fab | 2026-09-18 | 2026-10-16 |  | In Transit | Medium | 2026-10-04 | No tracking update for 5 days
SHP-1022 | DB Schenker | Inland | Haifa DC | Petah Tikva DC | 2026-10-05 | 2026-10-06 | 2026-10-06 | Delivered | Low | 2026-10-06 | Delivered on time
SHP-1023 | Expeditors | Air | Folsom, US | Haifa DC | 2026-10-08 | 2026-10-13 |  | Pending Pickup | Medium | 2026-10-08 | Awaiting export documents from supplier
SHP-1024 | DHL Global Forwarding | Air | Leixlip, IE | Kiryat Gat Fab | 2026-10-06 | 2026-10-09 |  | At Customs | High | 2026-10-09 | Hazmat documents under review
SHP-1025 | Kuehne+Nagel | Inland | Ashdod Port | Haifa DC | 2026-10-08 | 2026-10-10 |  | In Transit | Low | 2026-10-08 | On schedule